## Screen List
Screen List |  |  |  |  | Status
| Non-User | /user | index.html
about.html
contact-us.html
blog.html
course-list.html
course-detail.html
sign-in.html
sign-up.html
forgot.html
error-404.html
| Student | /student | student-dashboard.html | Home
|  |  | student-course-list.html | Course
student-course-resume.html
instructor-list.html
student-quiz.html
student-quiz-result.html
student-edit-profile.html
student-setting.html
course-detail-module.html
course-video-player.html
certificate.html
chat.html
|  | /instructor | instructor-dashboard.html
instructor- manage-course.html
instructor-create-course.html
instructor-quiz.html
instructor-studentlist.html
instructor-review.html
instructor-edit-profile.html
instructor-setting.html
chat.html
|  | /admin | admin-dashborad.html
admin-course-list.html
admin-course-category.html
admin-course-detail.html
|  |  | admin-student-list.html | Need student add Page.
|  |  | admin-instructor-list.html | Need instructor add Page.
admin-instructor-detail.html
admin-instructor-request.html
admin-review.html
admin-edit-profile.html
admin-setting.html
chat.html

## Folder Structure
static
/public
|  | assets | /css
/js
/vendor
| /private |  | /images
/profile
/instructor-profile
/student-profile
/admin-profile
/course-profile
/blog-profile
/course
/course-image-file
/course-video-file
/course-html-file
/blog
/blog-images
/blog-files
templates
/fragments
/darkmode-script.html
/script.html
/stylesheets.html
/user
/footer.html
/navbar.html
/layout.html
/main.html
/course-list.html
/course-detail.html
/blog-list.html
/blog.html
/contact-us.html
/about.html
/student
/student-navbar.html
/student-footer.html
/student-sidebar.html
/student-layout.html
/student-dashboard.html
/student-course-list.html
/student-course-resume.html
|  | /course-video-player.html | (Unrelated to fragments)
/student-certificate.html
/student-edit-profile.html
/forum.html
/instructor
/student-navbar.html
/student-footer.html
/student-sidebar.html
/instructor-layout.html
/instructor-dashboard.html
/instructor-manage-course.html
|  | /instructor-create-course.html | (No Side bar)
/instructor-create-quiz.html
/instructor-student-list.html
/instructor-edit-profile.html
/admin
/admin-navbar.html
/admin-sidebar.html
/admin-layout.html
/admin-dashboard.html
/adimin-course-list.html
/admin-course-category-list.html
/admin-student-list.html
/admin-instructor-list.html
/admin-instructor-request.html
/admin-view-blog.html
|  | /admin-create-blog.html | (No Fragment. Unique)
/admin-certificate-design.html
/admin-setting.html
/admin-edit-profile.html
src/main/java
/com/dat/learninghub/
/controller
/admin
/student
/instructor
/user
/service
/serviceImpl
/dto
/auth
/form
/model
/repository
/config
/security
/util
/auth

## Schedule
admin | admin-dashborad.html |  | Pending | Complete
admin-course-list.html
| admin-course-category.html | HWY
admin-course-detail.html
| admin-student-list.html | MMT
| admin-instructor-list.html | MMT
| admin-instructor-detail.html | MMT
admin-instructor-request.html
admin-layout
| admin-edit-profile.html | HWY
admin-certificate-detail
| admin-create-blog | MKZ
| admin-view-blog | MKZ
admin-create-course
admin-edit-course-detail
admin-navbar
admin-quiz
| admin-setting.html | WP
admin-sidebar.html

## Project Schedule
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
admin-dashborad.html | Third |  | Not started
admin-course-list.html | Third |  | Not started
admin-course-category.html | First | Hnin Wutt Yi | Not started
admin-course-detail.html | Third |  | Not started
admin-student-list.html | First | Myint Myat Thu | In progress
admin-instructor-list.html | First | Myint Myat Thu | In progress
admin-instructor-detail.html | First | Myint Myat Thu | Not started
admin-instructor-request.html | Third |  | Not started
admin-layout | Blocked | Myint Myat Thu | Completed
admin-edit-profile.html | First | khinekhinesoe7317@gmail.com | Not started
admin-certificate-design.html | First | khinekhinesoe7317@gmail.com | Not started
admin-view-blog.html | First | Kyaw Swar | Not started
admin-create-blog | First | Kyaw Swar | Not started
admin-create-course | Third |  | Not started
admin-edit-course-detail | Third |  | Not started
admin-navbar | Blocked |  | Completed
admin-quiz | Third |  | Not started
admin-setting.html | Completed | Wai Phone Aung | Completed
admin-sidebar.html | Blocked | Myint Myat Thu | Completed

## Status
Task | Status | Owner | Stage | Due date | Notes
index.html | Not 100%Completed(Read Note) | Wai Phone Aung | Already Taken | 2024-07-23 | need to change photo
about.html | Not 100%Completed(Read Note) | Wai Phone Aung | Already Taken | 2024-07-23 | need to change photo
contact-us.html | Not 100%Completed(Read Note) | Wai Phone Aung | Already Taken | 2024-07-23 | Need to change text in content
blog.html | Completed | Wai Phone Aung | Already Taken | 2024-07-23
course-list.html | Completed | Wai Phone Aung | Already Taken | 2024-07-23 | Still need footer
course-detail.html | Completed | Wai Phone Aung | Already Taken | 2024-07-23
sign-in.html | Completed | Wai Phone Aung | Already Taken | 2024-07-23
sign-up.html | Completed | Wai Phone Aung | Already Taken | 2024-07-23
change-password.html | Not 100%Completed(Read Note) | Myint Myat Thu | Already Taken | 2024-07-25 | Just Use the forget password .html page
forgot.html | Completed | Wai Phone Aung | Already Taken | 2024-07-23
Sudent Segment
student-dashboard.html | Completed | khinekhinesoe7317@gmail.com | Already Taken | 2024-07-24
student-course-list.html | Completed | khinekhinesoe7317@gmail.com | Already Taken | 2024-07-24
student-course-resume.html | Completed | khinekhinesoe7317@gmail.com | Already Taken | 2024-07-24
student-instructor-list.html | Completed | khinekhinesoe7317@gmail.com | Already Taken | 2024-07-25
student-quiz.html | Completed | khinekhinesoe7317@gmail.com | Already Taken | 2024-07-24 | need fix
student-quiz-result.html | Blocked | khinekhinesoe7317@gmail.com |  | 2024-07-24 | Decided not to show quiz result as separate html file. Show it on student quiz.
student-edit-profile.html | Completed | khinekhinesoe7317@gmail.com | Already Taken | 2024-07-24
student-setting.html | Blocked | hninwuttyi4321@gmail.com |  | 2024-07-24 | Not need. Not in RD
course-detail-module.html | Completed | hninwuttyi4321@gmail.com | Already Taken | 2024-07-24
course-module-material.html | Critical | Myint Myat Thu
course-video-player.html | Completed | hninwuttyi4321@gmail.com | Already Taken | 2024-07-25
certificate-list.html | In progress | Wai Phone Aung
certificate.html | Completed | Wai Phone Aung
chat.html |  |  | Already Taken | 2024-07-26
Instructor Segment
instructor-dashboard.html | Completed | hninwuttyi4321@gmail.com | Already Taken | 2024-07-24
instructor- manage-course.html | Completed | hninwuttyi4321@gmail.com | Already Taken | 2024-07-24
instructor-create-course.html | Completed | hninwuttyi4321@gmail.com | Already Taken | 2024-07-26
instructor-quiz.html | In progress | hninwuttyi4321@gmail.com
instructor-studentlist.html | Completed | hninwuttyi4321@gmail.com |  | 2024-07-24
instructor-review.html | In progress | mmyaatthum925@gmail.com
instructor-edit-profile.html | Completed | mmyaatthum925@gmail.com |  | 2024-07-25
instructor-setting.html | Blocked | mmyaatthum925@gmail.com |  |  | Not necessary and not in RD
chat.html |  | mmyaatthum925@gmail.com
Admin Segment
admin-dashborad.html | Completed | mmyaatthum925@gmail.com | Already Taken | 2024-07-25
admin-course-list.html | Completed | mmyaatthum925@gmail.com | Already Taken | 2024-07-25
admin-course-category.html | Completed | mmyaatthum925@gmail.com | Already Taken | 2024-07-25
admin-course-create-category.html | Not 100%Completed(Read Note) | Myint Myat Thu | Already Taken |  | Course Category CRUD is needed
admin-course-detail.html | Completed | kswar0566@gmail.com | Already Taken | 2024-07-25
admin-student-list.html | Not 100%Completed(Read Note) | kswar0566@gmail.com | Already Taken | 2024-07-25 | Admin student List will have modal bootstrap for CRUD
admin-instructor-list.html | Completed | kswar0566@gmail.com | Already Taken | 2024-07-25
admin-instructor-detail.html | Completed | kswar0566@gmail.com | Already Taken | 2024-07-25
admin-instructor-request.html | Completed | kswar0566@gmail.com | Already Taken | 2024-07-25
admin-review.html | Blocked | kswar0566@gmail.com |  | 2024-07-25
admin-edit-profile.html | Not 100%Completed(Read Note) | kswar0566@gmail.com | Already Taken | 2024-07-25 | Input Fields need to be set later.
admin-create-blog.html | Not 100%Completed(Read Note) | Myint Myat Thu | Already Taken | 2024-07-25 | CRUD will be made with modal
admin-setting.html | Not 100%Completed(Read Note) | kswar0566@gmail.com | Already Taken | 2024-07-25 | Input Fields need to be set later.
admin-report.html | Critical | Myint Myat Thu
Misc.
create-post.html | In progress | Myint Myat Thu